## PAUL
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 19:30 | 23:30 | Set up Express.js as the backend framework, set up MongoDb as primary database, write a database connection script create a database schema/models | 2,3,4,5,6,7 | Complete
Thursday Jan 30 2025 | 19:00 | 23:30 | Implement GET request to fetch data Implement POST request to insert data, Secure API endpoints with authentication middleware | 2,3,4,5,6,7 | Complete
Friday Jan 31 2025 | 10:15 | 11:30 | Use Postman for API testing, finalize organize backend code structure for future use | 2,3,4,5,6,7 | Complete
Friday Jan 31 2025 | 17:45 | 19:25 | Fix backend registration and login feedback, add in error messages | 2,3,4,5,6,7 | Complete
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 |  |  |  |  | SPRINT 4

## PRIYESH
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 20:30 | 23:30 | Creating a form for user signup & login, setting up authentification API, Connecting MongoDB database | 2, 3, 8, 10, 11, 13 | Complete
Thursday Jan 30 2025 | 19:30 | 23:30 | User stories creation + improvement, testing API endpoints with the database (using Postman), creating a team | 5, 17, 1, 19, 20 | Complete
Friday Jan 31 2025 | 17:45 | 19:25 | User stories on github, backend bug-fixing, assigning tasks for teammates | N/A | Complete
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 |  |  |  |  | SPRINT 4

## RIA
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 21:00 | 23:00 | Frontend code for user login and teams/channels, accessing channels depending on privileges | 2, 3, 4, 5, 6, 7 | Complete
Thursday Jan 30 2025 | 7:00 | 7:30 | Task Breakdown - Create tasks for specific user stories | 2, 3, 4, 5, 6, 8 | Complete
Friday Jan 31 2025 | 17:45 | 19:25 | Fixing Frontend CSS style | 2, 3, 4, 5, 6, 9 | Complete
Saturday Feb 1 2025 | 10:45 | 12:00 | Fixing Frontend CSS style + Adding Messages for Login Page | 2, 3, 4, 5, 6, 10 | Complete
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 |  |  |  |  | SPRINT 4

## MALIK
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 |  |  |  |  | SPRINT 4
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 19:30 | 23:30 | Frontend introduction | N/A | Complete
Wednesday Jan 29 2025 | 15:00 | 15:30 | Wrote ReadMe file | N/A | Complete
Thursday Jan 30 2025 | 20:00 | 20:30 | Filled out parts of the sprint plan/user stories | N/A | Complete
Friday Jan 31 2025 | 17:00 | 19:00 | Fill out User stories | N/A | Complete
Thursday Febuary 4 2025 | 19:40 | 20:00 | Filled out meeting minutes 1.2 | N/A | Complete
SPRINT 4

## ZAK
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
N/A
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 |  |  |  |  | SPRINT 4

## JUAN
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 19:30 | 23:30 | Frontend introduction | N/A | Complete
Thursday Jan 30, 2025 | 21:00 | 21:30 | Filling up, sprint plan/user stories | N/A | Complete
2025-01-31 | 18:30 | 18:50 | Create a new time log file and update information | N/A | Complete
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 |  |  |  |  | SPRINT 4