## PAUL
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 | [5 empty] | SPRINT 4
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 19:30 | 23:30 | Set up Express.js as the backend framework, set up MongoDb as primary database, write a database connection script create a database schema/models | 2,3,4,5,6,7 | Complete | Thursday Feb 20 2025 | 19:30 | 22:30 | Create the API endpoints for sending/retrieving DM messages (#49), integrate Socket.io for real-time chat updates (#50) | 49,50 | Complete | Friday Mar 14 2025 | 19:00 | 21:00 | Create colored status icons for every user status (#83) Status updates without needing page refresh (#84), Retrieve all users from databse (#85) | 83, 84, 85 | Complete
Thursday Jan 30 2025 | 19:00 | 23:30 | Implement GET request to fetch data Implement POST request to insert data, Secure API endpoints with authentication middleware | 2,3,4,5,6,7 | Complete | Tuesday Feb 25 2025 | 10:00 | 15:30 | Integrate Socket.io for real-time chat updates (#50), prevent unauthorized users by integrating secure sessions (#53) | 50,53 | Complete | Saturday Mar 15 2025 | 9:00 | 12:00 | Create API endpoit to update user status (#86), Integrate Socket.io for presence updates (#87), Store last seen timestamp to databse (#88) | 86,87,88 | Complete
Friday Jan 31 2025 | 10:15 | 11:30 | Use Postman for API testing, finalize organize backend code structure for future use | 2,3,4,5,6,7 | Complete | Wednesday Feb 26 2025 | 10:30 | 14:30 | Implement API endpoints to ensure messages are only retrivable by the sender and recipient for DM | 54 | Complete | Sunday Mar 16 2025 | 9:30 | 11:30 | Display Last Seen timestamp (#89), Create API to retrieve timestamp (#90) Update database to store last active time (#91) | 89,90,91 | Complete
Friday Jan 31 2025 | 17:45 | 19:25 | Fix backend registration and login feedback, add in error messages | 2,3,4,5,6,7 | Complete | Saturday Mar 1 2025 | 12:00 | 15:30 | Apply authentication checks before fetching for any message, if approved, the message is fetched | 55 | Complete | Monday Mar 17 2025 | 8:00 | 10:00 | Automatic timestamp update when user disconnects (#92), Allow DM even when user is offline (#93), User can view all messages once logged in (#94), | 92,93,94 | Complete
[6 empty] | Sunday Mar 2 2025 | 12:30 | 14:30 | Integrate Socket.io to ensure private communication using real-time authentication to limit chat visibility to only the source and destination prevent unauthorized users by | 56 | Complete | Tuesday Mar 18 2025 | 9:00 | 12:00 | Store messages in database until user logs in (#95), Create API to retrieve unread messages when user logs in (#96), Integrate socket.io for real-time message delivery when user comes online (#97) | 95,96,97

## PRIYESH
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 | [5 empty] | SPRINT 4
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 20:30 | 23:30 | Creating a form for user signup & login, setting up authentification API, Connecting MongoDB database | 2, 3, 8, 10, 11, 13 | Complete | Monday Feb 10 2025 | 22:00 | 22:30 | Create user stories & Tasks (word document) | N/A | Complete | Saturday Mar 8 2025 | 17:15 | 18:15 | Create user stories & Tasks (word document) | N/A | Complete | Saturday April 5 2025 | 10:00 | 17:00 | Working on the front-end and backend code for editing messages | 193-197 | Complete
Thursday Jan 30 2025 | 19:30 | 23:30 | User stories creation + improvement, testing API endpoints with the database (using Postman), creating a team | 5, 17, 1, 19, 20 | Complete | Sunday Feb 23 2025 | 17:00 | 23:00 | Coding the backend channels function (API endpoints, frontend connection for message display on server.js) + real-time updates | 44, 52, 53, 54, 56, 57, 58 | Complete | Saturday Mar 8 2025 | 14:00 | 15:00 | Added tasks into Github with proper labels, and descriptions for User Stories 11-15 | 119-141 | Complete | Sunday April 6 2025 | 14:00 | 18:00 | Working on the code for viewing editing history of the edited messages | 198-200 | Complete
Friday Jan 31 2025 | 17:45 | 19:25 | User stories on github, backend bug-fixing, assigning tasks for teammates | N/A | Complete | Monday Feb 24 2025 | 17:50 | 22:30 | Added in user stories from the word document & tasks to GitHub Issues + creating task descriptions (Issue #44, 45, 52, 53, 54, 56-65) + Create & Organize Github Projects page | 44, 45, 52, 53, 54, 56-65 | Complete | Monday Mar 10 2025 | 18:00 | 23:00 | Implementing code for the text-enhancements: Creating default channels for users. Implemented the front-end for the navigation bar and the default channel creation page. Also implemented appropriate backend API endpoints and Mongo scheme updates | 107, 117-120 | Complete | 2025-04-07 | 14:00 | 16:00 | Preparing presentation slides | N/A | Complete
[6 empty] | Wednesday Mar 05 2025 | 19:00 | 22:30 | Clean up and Github projects tab (table/board/roadmap) | N/A | Complete | Thursday Mar 13 2025 | 21:20 | 23:00 | Implementing code for the text-enhancements: Finish the "leave a channel" feature (backend implementation) + frontend and backend code implementation to request joining a private channel (button, request updates) - full frontend & backend implementation | 110, 111, 135-141 | Complete
[6 empty] | Thursday Mar 05 2025 | 22:00 | 23:45 | Create user acceptance tests for sprint 1 user stories | 88-93 | Complete | Saturday Mar 15 2025 | 14:15 | 14:30 | Connected the tasks to the user stories for User Stories 11-15 | 107-111, 119-141 | Complete
[12 empty] | Sunday Mar 16 2025 | 11:00 | 11:30 | Worked on the burndown chart to fill in all columns related to User Stories 11 to 15 | 107-111 | Complete
[12 empty] | Monday Mar 17 2025 | 21:00 | 22:20 | Merge the text-enhancements branch with the user presence & status | N/A | Complete
[12 empty] | Tuesday Mar 18 2025 | 21:45 | 22:45 | Merge the text-enhancements branch with the user presence & status | N/A | Complete
[12 empty] | Thursday Mar 20 2025 | 22:00 | 23:45 | Test the full functionality of the code + Ensure the meeting minutes follow the desired format and contain enough detail | N/A | Complete
[12 empty] | Friday Mar 21 2025 | 7:20 | 7:50 | Organize the Github Projects board (move from to-do/in progress to "Completed" for the necessary tasks) | N/A

## MALIK
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 |  |  |  |  | SPRINT 4
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 19:30 | 23:30 | Frontend introduction | N/A | Complete | Monday Feb 10 2025 | 20:00 | 21:00 | Writing Problem Statement and meeting minutes 2.1 | N/A | Complete | Monday Mar 17 2025 | 15:00 | 20:00 | Writing unit tests for server.js , and part of messaging.js | N/A | Complete | Monday April 7 2025 | 15:00 | 20:00 | Fixing some of the Unit test issues created through a merge with main | N/A | Complete
Wednesday Jan 29 2025 | 15:00 | 15:30 | Wrote ReadMe file | N/A | Complete | Wednesday Feb 12th 2025 | 21:00 | 21:30 | front end discussion/planning | N/A | Complete | Tuesday Mar 18 2025 | 14:00 | 1:00 | continued work on messaging.js, still incomplete , also tried implementing mentions , incomplete | 101 | Complete | Thursday April 10 2025 | 23:00 | 2:00 | Fixing some of the Unit test issues created through a merge with main + look into some new unit tests | N/A | Complete
Thursday Jan 30 2025 | 20:00 | 20:30 | Filled out parts of the sprint plan/user stories | N/A | Complete | Thursday Feb 13 2025 | 18:45 | 21:00 | Frontend - added chat page and some styling - buttons and chat box + basic chatting functionalities | 44,46 | Complete | Wednesday Mar 19 2025 | 14:00 | 18:00 | continued work on messaging.js, still incomplete again | 101 | Complete | Friday April 11 2025 | 14:00 | 17:00 | Fixing some of the Unit test issues + CICD Pipeline modification | N/A | Complete
Friday Jan 31 2025 | 17:00 | 19:00 | Fill out User stories | N/A | Complete | Friday Feb 14 2025 | 13:00 | 13:50 | Added CI/CD file with basic functionality | 79 | Complete | Thursday Mar 20 2025 | 20:00 | 2:00 | continued work on messaging.js, and on Ci/CD-Pipeline.yml | N/A | Complete | Friday April 11 2025 | 20:00 | 12:00 | Adding additional UNit tests for more minor functions | N/A | Complete
Thursday Febuary 4 2025 | 19:40 | 20:00 | Filled out meeting minutes 1.2 | N/A | Complete | Friday Feb 14 2025 | 13:50 | 14:20 | Created documentation for new issues, user stories and tasks, | N/A | Complete | Friday Mar 20 2025 | 11:30 | 13:00 | Updated Github workflows Ci/CD-Pipeline.yml file | N/A | Complete
[6 empty] | Friday Feb 21 2025 | 11:00 | 12:00 | Trying to fix the CI/CD branch - getting errors + research | 79 | Complete
[6 empty] | Wednesday Feb 25 2025 | 1:00 | 1:30 | Meeting minutes revision + Writing meeting minutes 2.2 | N/A | Complete
[6 empty] | Wednesday Mar 5 2025 | 16:30 | 18:30 | CI/CD implemented and further research + Added 2 Acceptance tests for issues 44 and 45 | 79,80,81 | Complete
[6 empty] | Friday Mar 7 2025 | 14:00 | 14:40 | Addes final acceptance tests for sprint 2 | 94,95 | Complete
[6 empty] | Friday Mar 7 2025 | 18:00 | 19:30 | Final sprint 2 adjustments - updated meeting minutes and discussion tab as TA recommmend | N/A | Complete

## ZAK
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 | [5 empty] | SPRINT 4
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Friday January 31 2025 | 19:00 | 20:00:00 PM | revised and tested code |  | complete | Thursday February 13 2025 | 19:00 | 23:00 | navigation bar front end, viewing channels + extra features (favorite/recent) | 50,51 | complete | Thursday March 13 2025 | 19:00 | 19:30 | added and implemented a logout button in the top right of the chat page screen, that lohgs out the user when they click on it | N/A | complete | Sunday march 30th | 14:00 | 16:00 | did research on how linters work and setup eslint | N/A | complete
[6 empty] | Friday February 21 2025 | 14:15 | 15:00 | welcome message, adding friends | 67 | complete | Saturday March 15 2025 | 11:00 | 11:20 | fixed the visibility of the error message now when when you enter wrong credentials you see an error message | N/A | complete | Wednsday april 9th | 16:00 | 20:00 | fixed 5 problems highlighted by linter, made commits in the repo and added a markdown file docummenting everything | N/A | complete
[6 empty] | Friday February 21 2025 | 15:00 | 16:30 | styling (eg, adding time for texts, dynamic chat box, , colors) | 53,65 | complete | Monday March17 2025 | 15:00 | 15:30 | fixed a bug: the functionality of the send button, now when you click on it the message gets sent | N/A | complete
[6 empty] | wednesday February 25 2025 | 1:00 | 2:00 | deleting messages feature | 61,60 | complete | Thursday March 20 2025 | 20:00 | 20:30 | added the about us page, a page with an introduction to our team and a link to our github repo | N/A | complete

## JUAN
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 | [5 empty] | SPRINT 4
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 19:30 | 23:30 | Frontend introduction | N/A | Complete | Sunday Feb 16 2025 | 12:00 | 14:00 | Dropdown menu work, displaying users available to chat, display channels available to chat. | 43,45 | Complete | 2025-03-12 | 14:00 | 15:00 | Making detailed meeting minutes (3.1) for absentees during the meeting. | N/A | Complete | 23-03-25 | 15:00 | 16:00 | Working on the display 'edited' label after an edited message | 21 | Complete
2025-01-30 | 21:00 | 21:30 | Filling up, sprint plan/user stories | N/A | Complete | Sunday Feb 16 2025 | 14:00 | 15:00 | Merging navigation bar and chat | N/A | Complete | 2025-03-17 | 18:00 | 20:00 | Experimenting with CI/CD pipeline, trying to get acquainted. | N/A | Complete | 2025-08-04 | 13:00 | 14:00 | Creating slides + pitch for presentation with the professor | N/A | Complete
2025-01-31 | 18:30 | 18:50 | Create a new time log file and update information | N/A | Complete | Sunday Feb 16 2025 | 19:00 | 22:00 | Update visual UI for all pages, implement a new style and creating a branch to upload all modifications | N/A | Complete | 2025-03-18 | 16:00 | 17:00 | Making detailed meeting minutes (3.2) for absentees during the meeting. | N/A | Complete | 2025-11-04 | 11:00 | 12:30 | Working on detailed UML diagram for final report | N/A | Complete
[6 empty] | Friday Feb 21 2025 | 13:45 | 15:00 | Minor UI modifications across members, admin and navigation bar | N/A | Complete | 2025-03-20 | 17:00 | 17:30 | Writing/Working on accpetance tests. | N/A | Complete

## RIA
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 | [5 empty] | SPRINT 4
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 21:00 | 23:00 | Frontend code for user login and teams/channels, accessing channels depending on privileges | 2, 3, 4, 5, 6, 7 | Complete | Tuesday Feb 11 2025 | 12:40 | 13:15 | User Stories 9 and 10/ Task Breakdown - Create user stories and tasks for specific user stories in a word doc | 46 and 47 55, 66-72 | Complete | Saturday March 8 2025 | 11:00 | 12:00 | User Stories 16 to 20/ Task Breakdown - Create user stories and tasks for specific user stories in a word doc | 142-167 | Complete | Thursday March 27 2025 | 13:00 | 13:30 | Research/Find a automatic tool for the five code bugs | N/A | Complete
Thursday Jan 30 2025 | 7:00 | 7:30 | Task Breakdown - Create tasks for specific user stories | 2, 3, 4, 5, 6, 8 | Complete | Friday Feb 21 2025 | 17:45 | 18:40 | Fixing CSS styling based on individual html pages (such as admin.html, index.html, admin.html, style,css and index.css) | N/A | Complete | Sunday March 9 2025 | 18:45 | 19:30 | Added tasks into Github with proper labels, and descriptions for User Stories 16-20 | 142-167 | Complete | Thursday March 27 2025 | 19:30 | 20:30 | User Story 21/ Task Breakdown - Create user stories and tasks for specific user stories in a word doc + added the tasks and user stories in GitHub | 192 - 201 | Complete
Friday Jan 31 2025 | 17:45 | 19:25 | Fixing Frontend CSS style | 2, 3, 4, 5, 6, 9 | Complete | Monday Feb 24 2025 | 18:45 | 22:00 | Added tasks into Github with proper labels, and descriptions and worked on Github projects (table/board) | 46 and 47 55, 66-72 | Complete | Saturday March 15 2025 | 19:45 | 20:30 | Worked on the burndown chart to fill in all columns related to User Stories 16 to 20 | 142-167 | Complete | Thursday March 27 2025 | 20:30 | 21:00 | Worked on the Projects page, putting in the tasks and their status + Worked/Created on acceptance tests for the user story + Worked on the burndown chart to fill in all columns related to User Story 21 | 192-203 | Complete
Saturday Feb 1 2025 | 10:45 | 12:00 | Fixing Frontend CSS style + Adding Messages for Login Page | 2, 3, 4, 5, 6, 10 | Complete | Tuesday March 4 2025 | 9:30 | 10:15 | Making the Frontend Homepage, including the server.js, added the bubble.gif, added the homepage.html, added homepage.js and edited script.js | N/A | Complete | Monday March 17 2025 | 19:00 | 21:00 | Worked on the Projects page, putting in the tasks and their status + worked/created on acceptance tests for each user story | 117-167 | Complete
[6 empty] | Thursday March 6 2025 | 19:00 | 21:00 | Addingg Comments on Discussions Page and Fixing the Repo by adding dates on the tasks in the Gitiub Projects | N/A | Complete