## Sheet1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Due date | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
2 & 3 | As a user, I want to be able to register and log in with my credentials so that I can access my account. | FE 1: Create a form for the user to log in (text boxes & button). FE 2: Style the login and sign-up forms for a user-friendly UI. BE 1: Set up authentication API for login | January 31st, 2025 | 3 | High | Low - Will not cause any substantial changes to the code that could break functionality. | Ria, Priyesh, Paul | 1 | FE Front End BE Back End
4 | As a logged-in user, I want to see my assigned team and channels so that I know where to communicate. | FE 1: Create a page where logged-in users can view their assigned team and channels. BE 1: Create API endpoint to fetch logged-in user’s assigned teams and channels. BE 2: Implement authentication and access control. | January 31st, 2025 | 2 | High | Low - Minimal changes required, mostly UI and API calls. | Ria, Priyesh, Paul | 1
5 | As an admin, I want to be able to create teams so that I can organize users into structured communication groups. | FE 1: Create a form for the admin to enter a team name and submit it. FE 2: Validate the form to ensure the team name is unique before submission. BE 1: Create POST API endpoint for admins to add a new team. BE 2: Check the server to see if a team name already exists (to prevent duplicates). | January 31st, 2025 | 3 | High | Low - Some validation required but overall straightforward. | Ria, Priyesh, Paul | 1
6 | As an admin, I want to be able to create channels for a team and assign users to them so that users can communicate in distinct channels. | FE 1: Create a form for the admin to enter a channel name and select the team it belongs to. FE 2: Validate that channel names are unique within a team. FE 3: Display a list of channels grouped by teams. BE 1: Create an API endpoint for admins to create a new channel BE 2: Create API endpoint to fetch channels grouped by teams BE 3: Assign users to channels (PUT) BE 3: Only allow admins access to create teams and channels (role-based control) | January 31st, 2025 | 4 | High | Medium - Role-based access required | Ria, Priyesh, Paul | 1
7 | As a logged-in user, I want to be able to see the channels & teams I am part of so that I can participate in discussions. | FE 1: Create a page where logged-in users can view their assigned team and channels. FE 2: Ensure that users can only see the teams and channels they belong to. FE 3 Update the UI dynamically based on the user’s role (admin vs. regular user). BE 1: Create API endpoint to fetch logged-in user’s assigned teams and channels. BE 2: Implement authentication and access control. BE 3: Fetch and return the user’s role from the database. | February 2nd, 2025 | 2 | High | Low - Mostly API and UI updates with some role-based logic. | Ria, Priyesh, Paul | 1
FE = Front-end BE = Back-end