## Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Due date | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
2 & 3 | As a user, I want to be able to register and log in with my credentials so that I can access my account. | FE 1: Create a form for the user to log in (text boxes & button). FE 2: Style the login and sign-up forms for a user-friendly UI. BE 1: Set up authentication API for login | January 31st, 2025 | 3 | High | Low - Will not cause any substantial changes to the code that could break functionality. | Ria, Priyesh, Paul | 1 | FE Front End BE Back End
4 | As a logged-in user, I want to see my assigned team and channels so that I know where to communicate. | FE 1: Create a page where logged-in users can view their assigned team and channels. BE 1: Create API endpoint to fetch logged-in user’s assigned teams and channels. BE 2: Implement authentication and access control. | January 31st, 2025 | 2 | High | Low - Minimal changes required, mostly UI and API calls. | Ria, Priyesh, Paul | 1
5 | As an admin, I want to be able to create teams so that I can organize users into structured communication groups. | FE 1: Create a form for the admin to enter a team name and submit it. FE 2: Validate the form to ensure the team name is unique before submission. BE 1: Create POST API endpoint for admins to add a new team. BE 2: Check the server to see if a team name already exists (to prevent duplicates). | January 31st, 2025 | 3 | High | Low - Some validation required but overall straightforward. | Ria, Priyesh, Paul | 1
6 | As an admin, I want to be able to create channels for a team and assign users to them so that users can communicate in distinct channels. | FE 1: Create a form for the admin to enter a channel name and select the team it belongs to. FE 2: Validate that channel names are unique within a team. FE 3: Display a list of channels grouped by teams. BE 1: Create an API endpoint for admins to create a new channel BE 2: Create API endpoint to fetch channels grouped by teams BE 3: Assign users to channels (PUT) BE 3: Only allow admins access to create teams and channels (role-based control) | January 31st, 2025 | 4 | High | Medium - Role-based access required | Ria, Priyesh, Paul | 1
7 | As a logged-in user, I want to be able to see the channels & teams I am part of so that I can participate in discussions. | FE 1: Create a page where logged-in users can view their assigned team and channels. FE 2: Ensure that users can only see the teams and channels they belong to. FE 3 Update the UI dynamically based on the user’s role (admin vs. regular user). BE 1: Create API endpoint to fetch logged-in user’s assigned teams and channels. BE 2: Implement authentication and access control. BE 3: Fetch and return the user’s role from the database. | February 2nd, 2025 | 2 | High | Low - Mostly API and UI updates with some role-based logic. | Ria, Priyesh, Paul | 1

## Sprint 2
Issue # | User Story Title/Task Title | Description/Associated Tasks | Tasks Issue Numbers | Due date | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
44 | As a logged-in user, I want to send messages in a channel so that all the members of that channel can view & participate in the conversation | FE 1: Create a navigation bar UI element Add issue numbers (Task #28) FE 2: Create buttons to select channels (Task #29) FE 3: Create chat page (Task #30) FE 4: Create input field box for messages (Task #31) FE 5: Create a send button (Task #32) FE 6: Display real-time messages (Task #33) BE 1: Create API endpoint to retrieve channels (Task #34) BE 2: Create API endpoint to retrieve channel messages (Task #35) BE 3: Create API endpoint to send messages (Task #36) BE 4: Implement real-time messages (Task #37) | 50-59 | Friday March 7th, 2025 | 5 | High | Medium - Real-time updates and handling concurrent issues may cause data storage problems | FE: Malik, Juan, Zack, Ria BE: Priyesh | 2
45 | As an admin, I want to delete messages, so that the group communication remains respectful and adheres to community guidelines. | FE 1: Display delete option for admins (Task #38) FE 2: Create a confirmation message for deleting messages (Task #39) FE 3: Update UI for deleted messages in real-time. (Task #40) BE 1: Create API endpoint for message deletion (Task #41) BE 2: Implement real-time updates for deletion (Task #42) | 59-65 | Friday March 7th, 2025 | 3 | High | Low - Minimal changes required - DELETE api call | FE: Malik, Juan, Zack, Ria BE: Priyesh | 2
46 | As a logged-in user, I want to send private messages to another user to have direct conversations securely. | FE 1: Button to select the user (Task #45) FE 2: Input field to type message (Task #45) FE 3: Button to send messages (Task #47) FE 4: Real-time updates (Task #48) BE 1: API endpoints for sending & retrieving DMs (Task #49) BE 2: SocketIO integration for real-time updates (Task #50) | 55, 67-69, 70-72 | Friday March 7th, 2025 | 5 | High | Medium - Data storage and appropriate fetching of data | FE: Malik, Juan, Zack, Ria BE: Paul | 2
47 | As a logged-in user, I want my direct messages to be private so that only the intended recipient and I can see our conversation. | .FE 1: Only the sender and recipient can view the conversation. (Task #52) BE 1: Secure session handling to prevent unauthorized access. (Task #53) BE 2: API endpoint ensuring messages are only retrievable by the sender and recipient. (Task #54) BE 3: Authentication checks before fetching messages. (Task #55) BE 4: SocketIO Integration for real-time updates while maintaining privacy. (#56) | 74-78 | Friday March 7th, 2025 | 4 | High | Medium - Role-based access required along with authentification verification | FE: Malik, Juan, Zack, Ria BE: Paul | 2