## PAUL
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 | [5 empty] | SPRINT 4
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 19:30 | 23:30 | Set up Express.js as the backend framework, set up MongoDb as primary database, write a database connection script create a database schema/models | 2,3,4,5,6,7 | Complete | Thursday Feb 20 2025 | 19:30 | 22:30 | Create the API endpoints for sending/retrieving DM messages (#49), integrate Socket.io for real-time chat updates (#50) | 49,50 | Complete
Thursday Jan 30 2025 | 19:00 | 23:30 | Implement GET request to fetch data Implement POST request to insert data, Secure API endpoints with authentication middleware | 2,3,4,5,6,7 | Complete | Tuesday Feb 25 2025 | 10:00 | 15:30 | Integrate Socket.io for real-time chat updates (#50), prevent unauthorized users by integrating secure sessions (#53) | 50,53 | Complete
Friday Jan 31 2025 | 10:15 | 11:30 | Use Postman for API testing, finalize organize backend code structure for future use | 2,3,4,5,6,7 | Complete | Wednesday Feb 26 2025 | 10:30 | 14:30 | Implement API endpoints to ensure messages are only retrivable by the sender and recipient for DM | 54 | Complete
Friday Jan 31 2025 | 17:45 | 19:25 | Fix backend registration and login feedback, add in error messages | 2,3,4,5,6,7 | Complete | Saturday Mar 1 2025 | 12:00 | 15:30 | Apply authentication checks before fetching for any message, if approved, the message is fetched | 55 | Complete
[6 empty] | Sunday Mar 2 2025 | 12:30 | 14:30 | Integrate Socket.io to ensure private communication using real-time authentication to limit chat visibility to only the source and destination prevent unauthorized users by | 56 | Complete

## PRIYESH
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 | [5 empty] | SPRINT 4
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 20:30 | 23:30 | Creating a form for user signup & login, setting up authentification API, Connecting MongoDB database | 2, 3, 8, 10, 11, 13 | Complete | Monday Feb 10 2025 | 22:00 | 22:30 | Create user stories & Tasks (word document) | N/A | Complete
Thursday Jan 30 2025 | 19:30 | 23:30 | User stories creation + improvement, testing API endpoints with the database (using Postman), creating a team | 5, 17, 1, 19, 20 | Complete | Sunday Feb 23 2025 | 17:00 | 23:00 | Coding the backend channels function (API endpoints, frontend connection for message display on server.js) + real-time updates | 44, 52, 53, 54, 56, 57, 58 | Complete
Friday Jan 31 2025 | 17:45 | 19:25 | User stories on github, backend bug-fixing, assigning tasks for teammates | N/A | Complete | Monday Feb 24 2025 | 17:50 | 22:30 | Added in user stories from the word document & tasks to GitHub Issues + creating task descriptions (Issue #44, 45, 52, 53, 54, 56-65) + Create & Organize Github Projects page | 44, 45, 52, 53, 54, 56-65 | Complete
[6 empty] | Saturday Mar 2 2025 | 10:30 | 15:00 | Merge channel code with DM code + add delete backend functionality with the database (API endpoints) & connect front-end for deletion | 37, 41-46 | Complete
[6 empty] | Wednesday Mar 5 2025 | 19:00 | 22:30 | Clean up and Github projects tab (table/board/roadmap) | N/A | Complete
[6 empty] | Thursday Mar 6 2025 | 22:00 | 23:45 | Create user acceptance tests for sprint 1 user stories | 88-93 | Complete

## MALIK
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 |  |  |  |  | SPRINT 4
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 19:30 | 23:30 | Frontend introduction | N/A | Complete | Monday Feb 10 2025 | 20:00 | 21:00 | Writing Problem Statement and meeting minutes 2.1 | N/A | Complete
Wednesday Jan 29 2025 | 15:00 | 15:30 | Wrote ReadMe file | N/A | Complete | Wednesday Feb 12th 2025 | 21:00 | 21:30 | front end discussion/planning | N/A | Complete
Thursday Jan 30 2025 | 20:00 | 20:30 | Filled out parts of the sprint plan/user stories | N/A | Complete | Thursday Feb 13 2025 | 18:45 | 21:00 | Frontend - added chat page and some styling - buttons and chat box + basic chatting functionalities | 44,46 | Complete
Friday Jan 31 2025 | 17:00 | 19:00 | Fill out User stories | N/A | Complete | Friday Feb 14 2025 | 13:00 | 13:50 | Added CI/CD file with basic functionality | 79 | Complete
Thursday Febuary 4 2025 | 19:40 | 20:00 | Filled out meeting minutes 1.2 | N/A | Complete | Friday Feb 14 2025 | 13:50 | 14:20 | Created documentation for new issues, user stories and tasks, | N/A | Complete
[6 empty] | Friday Feb 21 2025 | 11:00 | 12:00 | Trying to fix the CI/CD branch - getting errors + research | 79 | Complete
[6 empty] | Wednesday Feb 25 2025 | 1:00 | 1:30 | Meeting minutes revision + Writing meeting minutes 2.2 | N/A | Complete
[6 empty] | Wednesday Mar 5 2025 | 16:30 | 18:30 | CI/CD implemented and further research + Added 2 Acceptance tests for issues 44 and 45 | 79,80,81 | Complete
[6 empty] | Friday Mar 7 2025 | 14:00 | 14:40 | Addes final acceptance tests for sprint 2 | 94,95 | Complete
[6 empty] | Friday Mar 7 2025 | 18:00 | 19:30 | Final sprint 2 adjustments - updated meeting minutes and discussion tab as TA recommmend | N/A | Complete

## ZAK
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 | [5 empty] | SPRINT 4
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
N/A | [5 empty] | Thursday February 13 2025 | 19:00 | 23:00 | navigation bar front end, viewing channels + extra features (favorite/recent) | 50,51 | complete
[6 empty] | Friday February 21 2025 | 14:15 | 15:00 | welcome message, adding friends | 67 | complete
[6 empty] | Friday February 21 2025 | 15:00 | 16:30 | styling (eg, adding time for texts, dynamic chat box, , colors) | 53,65 | complete
[6 empty] | wednesday February 25 2025 | 1:00 | 2:00 | deleting messages feature | 61,60 | complete

## JUAN
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 | [5 empty] | SPRINT 4
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 19:30 | 23:30 | Frontend introduction | N/A | Complete | Sunday Feb 16 2025 | 12:00 | 14:00 | Dropdown menu work, displaying users available to chat, display channels available to chat. | 43,45 | Complete
2025-01-30 | 21:00 | 21:30 | Filling up, sprint plan/user stories | N/A | Complete | Sunday Feb 16 2025 | 14:00 | 15:00 | Merging navigation bar and chat | N/A | Complete
2025-01-31 | 18:30 | 18:50 | Create a new time log file and update information | N/A | Complete | Sunday Feb 16 2025 | 19:00 | 22:00 | Update visual UI for all pagaes, implement a new style and creating a branch to upload all modifications | N/A | Complete
[6 empty] | Friday Feb 21 2025 | 13:45 | 15:00 | Minor UI modifications across members, admin and navigation bar | N/A | Complete

## RIA
SPRINT 1 | [5 empty] | SPRINT 2 | [5 empty] | SPRINT 3 | [5 empty] | SPRINT 4
Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS | Date | Start Time | End Time | Task | ISSUE # | STATUS
Wednesday Jan 29 2025 | 21:00 | 23:00 | Frontend code for user login and teams/channels, accessing channels depending on privileges | 2, 3, 4, 5, 6, 7 | Complete | Tuesday Feb 11 2025 | 12:40 | 13:15 | User Stories 9 and 10/ Task Breakdown - Create user stories and tasks for specific user stories in a word doc | 46 and 47 55, 66-72 | Complete
Thursday Jan 30 2025 | 7:00 | 7:30 | Task Breakdown - Create tasks for specific user stories | 2, 3, 4, 5, 6, 8 | Complete | Friday Feb 21 2025 | 17:45 | 18:40 | Fixing CSS styling based on individual html pages (such as admin.html, index.html, admin.html, style,css and index.css) | N/A | Complete
Friday Jan 31 2025 | 17:45 | 19:25 | Fixing Frontend CSS style | 2, 3, 4, 5, 6, 9 | Complete | Monday Feb 24 2025 | 18:45 | 22:00 | Added tasks into Github with proper labels, and descriptions and worked on Github projects (table/board) | 46 and 47 55, 66-72 | Complete
Saturday Feb 1 2025 | 10:45 | 12:00 | Fixing Frontend CSS style + Adding Messages for Login Page | 2, 3, 4, 5, 6, 10 | Complete | Tuesday March 4 2025 | 9:30 | 10:15 | Making the Frontend Homepage, including the server.js, added the bubble.gif, added the homepage.html, added homepage.js and edited script.js | N/A | Complete
[6 empty] | Thursday March 6 2025 | 19:00 | 21:00 | Addingg Comments on Discussions Page and Fixing the Repo by adding dates on the tasks in the Gitiub Projects | N/A | Complete