## Sprint 1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Due date | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
2 & 3 | As a user, I want to be able to register and log in with my credentials so that I can access my account. | FE 1: Create a form for the user to log in (text boxes & button). FE 2: Style the login and sign-up forms for a user-friendly UI. BE 1: Set up authentication API for login | January 31st, 2025 | 3 | High | Low - Will not cause any substantial changes to the code that could break functionality. | Ria, Priyesh, Paul | 1 | FE Front End BE Back End
4 | As a logged-in user, I want to see my assigned team and channels so that I know where to communicate. | FE 1: Create a page where logged-in users can view their assigned team and channels. BE 1: Create API endpoint to fetch logged-in user’s assigned teams and channels. BE 2: Implement authentication and access control. | January 31st, 2025 | 2 | High | Low - Minimal changes required, mostly UI and API calls. | Ria, Priyesh, Paul | 1
5 | As an admin, I want to be able to create teams so that I can organize users into structured communication groups. | FE 1: Create a form for the admin to enter a team name and submit it. FE 2: Validate the form to ensure the team name is unique before submission. BE 1: Create POST API endpoint for admins to add a new team. BE 2: Check the server to see if a team name already exists (to prevent duplicates). | January 31st, 2025 | 3 | High | Low - Some validation required but overall straightforward. | Ria, Priyesh, Paul | 1
6 | As an admin, I want to be able to create channels for a team and assign users to them so that users can communicate in distinct channels. | FE 1: Create a form for the admin to enter a channel name and select the team it belongs to. FE 2: Validate that channel names are unique within a team. FE 3: Display a list of channels grouped by teams. BE 1: Create an API endpoint for admins to create a new channel BE 2: Create API endpoint to fetch channels grouped by teams BE 3: Assign users to channels (PUT) BE 3: Only allow admins access to create teams and channels (role-based control) | January 31st, 2025 | 4 | High | Medium - Role-based access required | Ria, Priyesh, Paul | 1
7 | As a logged-in user, I want to be able to see the channels & teams I am part of so that I can participate in discussions. | FE 1: Create a page where logged-in users can view their assigned team and channels. FE 2: Ensure that users can only see the teams and channels they belong to. FE 3 Update the UI dynamically based on the user’s role (admin vs. regular user). BE 1: Create API endpoint to fetch logged-in user’s assigned teams and channels. BE 2: Implement authentication and access control. BE 3: Fetch and return the user’s role from the database. | February 2nd, 2025 | 2 | High | Low - Mostly API and UI updates with some role-based logic. | Ria, Priyesh, Paul | 1

## Sprint 2
Issue # | User Story Title/Task Title | Description/Associated Tasks | Tasks Issue Numbers | Due date | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
44 | As a logged-in user, I want to send messages in a channel so that all the members of that channel can view & participate in the conversation | FE 1: Create a navigation bar UI element Add issue numbers (Task #28) FE 2: Create buttons to select channels (Task #29) FE 3: Create chat page (Task #30) FE 4: Create input field box for messages (Task #31) FE 5: Create a send button (Task #32) FE 6: Display real-time messages (Task #33) BE 1: Create API endpoint to retrieve channels (Task #34) BE 2: Create API endpoint to retrieve channel messages (Task #35) BE 3: Create API endpoint to send messages (Task #36) BE 4: Implement real-time messages (Task #37) | 50-59 | Friday March 7th, 2025 | 5 | High | Medium - Real-time updates and handling concurrent issues may cause data storage problems | FE: Malik, Juan, Zack, Ria BE: Priyesh | 2
45 | As an admin, I want to delete messages, so that the group communication remains respectful and adheres to community guidelines. | FE 1: Display delete option for admins (Task #38) FE 2: Create a confirmation message for deleting messages (Task #39) FE 3: Update UI for deleted messages in real-time. (Task #40) BE 1: Create API endpoint for message deletion (Task #41) BE 2: Implement real-time updates for deletion (Task #42) | 59-65 | Friday March 7th, 2025 | 3 | High | Low - Minimal changes required - DELETE api call | FE: Malik, Juan, Zack, Ria BE: Priyesh | 2
46 | As a logged-in user, I want to send private messages to another user to have direct conversations securely. | FE 1: Button to select the user (Task #45) FE 2: Input field to type message (Task #45) FE 3: Button to send messages (Task #47) FE 4: Real-time updates (Task #48) BE 1: API endpoints for sending & retrieving DMs (Task #49) BE 2: SocketIO integration for real-time updates (Task #50) | 55, 67-69, 70-72 | Friday March 7th, 2025 | 5 | High | Medium - Data storage and appropriate fetching of data | FE: Malik, Juan, Zack, Ria BE: Paul | 2
47 | As a logged-in user, I want my direct messages to be private so that only the intended recipient and I can see our conversation. | .FE 1: Only the sender and recipient can view the conversation. (Task #52) BE 1: Secure session handling to prevent unauthorized access. (Task #53) BE 2: API endpoint ensuring messages are only retrievable by the sender and recipient. (Task #54) BE 3: Authentication checks before fetching messages. (Task #55) BE 4: SocketIO Integration for real-time updates while maintaining privacy. (#56) | 74-78 | Friday March 7th, 2025 | 4 | High | Medium - Role-based access required along with authentification verification | FE: Malik, Juan, Zack, Ria BE: Paul | 2

## Sprint3
Issue # | User Story Title/Task Title | Description/Associated Tasks | Tasks Issue Numbers | Due date | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
107 | Default Channels for All Users | FE1: Create a page where logged-in users can view default channels (Task #57) FE2: Display default channels dynamically on the UI (Task #58) BE1: Create API endpoints to fetch the list of default channels (Task #59) BE2: API endpoints for default channel data (Task #60) | 117-120 | 2025-03-21 | 5 | High | Medium - Additional real-time updates and handling concurrent issues may cause data storage problems. | FE: Malik BE: Priyesh | 3
108 | Private Channel Creation | FE1: Implement a UI feature to allowusers to create private channels (Task #61) FE2: Display a list of private channels the user is a memeber of (Task #62) BE1: Create API endpoints for private channel creation (Task #63) BE2: API endpoint to store private channel messages in the database (POST) (Task #64) BE3: API endpoint to store private channel members in the database (POST) (Task #65) | 121-125 | 2025-03-21 | 4 | High | High - Ensuring secure storage of private messages and members while maintaining real0time updates could lead to synchronization and access control issues | FE:Ria BE: Priyesh | 3
109 | Inviting Users to Private Channels | FE1: Create an invite button in private channels (Task #66) FE2: Display a list of users who have been invited (Task #67) FE3: Show an interface for users to accept or decline invitations (Task #68) BE1: API endpoint for sending invitations (Task #69) BE2: API endpoint for receiving invitations (Task #70) BE3: Implement access control to ensure only invited users can join (Task #71) | 126-131 | 2025-03-21 | 5 | High | High - Managing invitation handling, real-time UI updates, and ensuring that only invited users join without bypassing restrictions may pose security risks | FE: Ria BE: Priyesh | 3
110 | Leaving a Channel | FE1: Add a leave channel button in private channels (Task #72) FE2: Display a confirmation prompt before leaving (Task #73) FE3: Ensure the UI updates dynamically when a user leaves (Task #74) BE1: Create an API endpoint to handle user removal from channels (Task #75) BE2: Ensure past messages from the user remain visible after a user leaves (Task #76) | 132-136 | 2025-03-21 | 4 | High | Medium - Ensuring proper user removal without leaving inconsistencies in data and real-time UI updates might introduce potential data integrity concerns. | FE: Malik BE: Priyesh | 3
111 | Requesting to Join a Private Channel | FE1: Implement a "Request to Join" button for private channels (Task #77) FE2: Display a list of pending join requests for the channel creator (Task #78) FE3: Show approval & rejection options for the creator (Task #79) BE1: Create an API endpoints to handle join requests (Task #80) BE2: Implement code to add approved users to the channel (Task #81) | 137-141 | 2025-03-21 | 5 | High | High - Handling user requests, approvals, and rejections securely while maintaining seamless real-time updates may lead to access control vulnerabilities. | FE: Malik, Ria BE: Priyesh | 3
112 | User Presence Indicators | FE1: User dashboard displaying all registered users (Task #82) FE2: Colored status icons next to usernames (🟢 Online, 🟡 Away, ⚪ Offline) (Task #83) FE3: Status updates without needing a page refresh (Task #84) BE1: Status updates without needing a page refresh (Task #84) BE2: Retrieve all users from the database (Task #85) BE3: API endpoint to fetch and update user status based on activity (Task #86) BE4: Socket.io integration for real-time presence updates (Task #87) BE5: Database update to store last seen timestamps and current status (Task #88) | 142-48 | 2025-03-21 | 4 | High | High - Real-time status updates may lead to performance bottlenecks and increased server load. Synchronization issues could cause incorrect status displays. | FE: Ria BE: Paul | 3
113 | Last Seen Timestamp | FE1: Display last seen timestamp (Task #89) BE1: API to store and retrieve the last activity timestamp (Task #90) BE2: Database schema update to store last active time (Task #91) BE3: Automatic update of the last seen timestamp when a user logs out or disconnects (Task #92) | 149-152 | 2025-03-21 | 5 | High | Medium - Ensuring accurate last seen timestamps while handling frequent logins/logouts and disconnections may introduce inconsistencies in the database. | FE: Ria BE: Paul | 3
114 | Sending Messages to Offline Users | FE1: Allow message sending even if the recipient is Offline (Task #93) FE2: User can view all stored messages once logged in (Task #94) BE1: Messages should be stored in the database until the recipient logs in (Task #95) BE2: API endpoint to retrieve unread messages when a user logs in (Task #96) BE3: Socket.io integration for real-time message delivery when the recipient comes online (Task #97) | 153-157 | 2025-03-21 | 2 | High | High - Storing and delivering messages reliably when users come online requires robust database management and real-time event handling to prevent message loss or duplication. | FE: Malik BE: Paul | 3

## Sprint 4
Issue # | User Story Title/Task Title | Description/Associated Tasks | Tasks Issue Numbers | Due date | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
115 | Emoji Support in Messages | FE1: Rendered emojis appear in messages (Task #98) BE1: API support for storing and retrieving emojis in messages (Task #99) BE2: Socket.io updates for real-time emoji reactions (Task #100) | 158 - 160 | 2025-03-21 | 2 | High | Low - Storing and rendering emojis should be straightforward, but ensuring consistent display across devices and handling real-time emoji reactions may introduce minor UI challenges. | FE: Malik BE: Paul | 4
116 | Quoting Messages Using @ + Reply | FE1: Message input field with @mention support (Task #101) FE2: Quoted message preview appears above the input field before sending (Task #102) FE3: Clickable quoted messages that scroll to the original message (Task #103) BE1: API endpoint to send messages with a quotedMessageId (Task #104) BE2: Database schema update to store message references for quoting (Task #105) BE3: API endpoint to retrieve the original quoted message when loading a reply (Task #106) BE4: WebSocket/Socket.io integration for real-time quoted messages (Task #107) | 161 - 167 | 2025-03-21 | 5 | High | Medium - Storing quoted messages efficiently while ensuring quick retrieval and proper UI rendering may lead to potential database performance concerns. | FE: Malik BE: Paul | 4